## Overview of Workflow
CASA of Santa Cruz County Annual Fundraiser-Workflow and Timeline
Week | Start Date or Deadline | Action | Responsibility | Name
22 | 2013-05-06 | Recruit event committee from Board, FOC, and community. | ED
20 | 2013-05-20 | Begin planning event. Decide format, theme, entertainment, budget (including ticket price) and menu. | ED, Event committee
19 | 2013-05-27 | Assign members and identify roles for subcommittees: • Silent auction, • Live auction, • Program, • Décor, • Logistics, and • Others as needed. | Chair | Mary S
19 | 2013-05-27 | Begin process of design and production of printed material: Save the date card, invitation, and other material as needed. | Chair | Mary S
19 | 2013-05-27 | Begin soliciting sponsors for event | DD
19 | 2013-05-27 | Plan and manage publicity | DD
19 | 2013-05-27 | Identify items desired and persons to solicit. Obtain and distribute four-part donation forms, solicitation materials, thank-you letters. | Silent Auction | Lynn
16 | 2013-06-10 | Identify auctioneer and confirm | Chair | Mary S
16 | 2013-06-10 | Identify and solicit approximately eight items for the live auction. | Live Auction | Mary D
16 | 6/10/2013 ongoing | • Review donation forms include all information necessary to describe item, retail value, and necessary donor information. • Find out whether we actually have the item and, if not, tell Silent Auction chair that it needs to be picked up. • Transcribe information from donation form to a master spreadsheet (prepare new sheet based upon previous year’s sheet.) • Set up file for each item and file by category. • Make gift certificate for items that need one and note this on the spreadsheet. | OC | Cita, Katie
16 | 2013-06-10 | Identify and confirm entertainer(s) | Program | Melanie
16 | 2013-06-10 | Secure storage area for auction items | Silent Auction | Lynn
16 | 6/10/2013 ongoing | Items begin to come in. Silent auction chair will assign persons and times for storage to be open to accept items. Items to be delivered to storage area by soliciting person, the donor, or staff at the designated times. Each item must have donation form attached. Form must include all information called for on the form. Donor gets goldenrod copy of the form. Pink copy attached to item. White and yellow copies go to OC. | Silent Auction | Lynn
11 | 2013-07-16 | Save the date card mailed | DD, OC | Cita
11 | 2013-07-15 | Tour venue and make preliminary plans for décor. | Décor | Jenni
8 | 2013-08-05 | Confirm menu with venue personnel | Chair | Mary S
8 | 2013-08-05 | Obtain "Best of the Board" bottles for auction and deliver to storage area | Chair | Lonnie
8 | 2013-08-05 | Obtain wine to drink at event | Designee | Marilyn K
8 | 2013-08-05 | Design "wine cellar" raffle and obtain wine. | FOC | Anne Young
8 | 2013-08-05 | Finalize program. Begin rehearsing presenters. Meet with AV person to plan video presentation. Check with Chair about audio equipment at the venue. | Program | Melanie
7 | 2013-08-12 | Invitations mailed | Staff | Cita
6 | 2013-08-15 | Receive guest responses, assign tables, keep ED and Chair informed of ticket sales progress. Assign bidder numbers, design and produce programs, name tags. | Staff | Mary K, Cita, Katie. Marilyn will check with Cynthia about determining if there are any "toxic" combinations to be avoided in assigning table seating.
6 | 2013-08-15 | Decide final décor, report linen selection to venue. Obtain materials and begin preparing decorations. | Décor | Jenni
| 2013-08-30 | Recruit volunteers for day-of duties:
|  | 4 people/2 trucks to transport items from storage and set up lattice background/support structure if needed for hanging artwork or other posters. (Check with Jeff Talmadge to obtain the lattice.) |  | Kent, Kenneth Coale, Harry Smeek, need one more.
|  | 10 people to be at Chaminade to make sure auction item tables are set up where we want them, install table signs, arrange silent auction items, arrange live auction posters and raffle posters on easels/lattice. |  | Marilyn Koll, Susan Coale, need 8 more
|  | 2 people to pick up snacks and deliver to the volunteers setting up the auction tables. |  | need 2
|  | 2-3 people to stage silent auction display |  | Kim Furman, Gale Topping, Lori Doan, Adele Talmadge usually do this. Marilyn has confirmed for 2013.
|  | 4 people to install décor |  | Jenni, Marilyn M. need two more.
|  | 8 board members to greet (2/each half hour) . |  | Susan will solicit at board meeting
2 people (one board/one Friend) to greet guests at the ballroom and direct them to their tables
All board members are asked to serve as ushers to direct guests upstairs when silent auction closes.
|  | 10 people to be spotters in the ballroom during the live auction. |  | Ken Koll, Kenneth Coale, need 8 more tall people.
|  | 6 people to clean up | Logistics | Susan will solicit at board meeting and from staff and staff friends.
4 | 2013-08-31 | Ensure all auction items picked up and delivered to storage with pink copy of donation form attached. | Silent Auction | Lynn will tell Mary S when there are items that need to be picked up
3 | 2013-09-09 | Work with logistics, silent auction, live auction, program, and decor committee chairs to determine table layout, easels, umbrellas, café tables and chairs and audio equipment required for patio; determine layout and audio/visual equipment required for dining room and layout for check out area. | Chair | Mary S.
3 | 2013-09-09 | Determine how to display the live auction items on the patio and in the slide show to be shown in the ballroom. Obtain materials and create displays. Determine how to secure the posters to the easels and how to keep the easels from tipping over in the wind. | Logistics | Mary K, Mary S, Cita, Marilyn. Marilyn will check with Jeff Talmadge about where and how to obtain lattice framework. Kent will obtain sandbags as ballast for the easels.
3 | 2013-09-09 | Access all CASA-owned auction supplies, including metal sign holders for silent auction tables; examine; transport to auction storage site and ready for transport on day of event. | Logistics | Cita and Katie will retrieve from Anne's house. Susan will examine and ensure transport to storage
3 | 2013-09-09 | Meet at auction storage to view items and decide how to display and what materials are needed for display. Note materials needed on the master spreadsheet. Decide upon auction categories and determine layout of auction tables. | Silent Auction | Lynn, Marilyn K, Cita, and others
3 | 2013-09-09 | When the list of auction items is finalized: • Assign a number to each item (Category letter followed by number, e.g., J-1 for first jewelry item) • Determine starting bid • Determine minimum raise • Note any major restrictions (as use-by date, or day of the week limitations) • Ensure accurate spellings • Create alphabetized list of donors for the program | Staff | Cita and Katie
2 | 2013-09-13 | Obtain all materials needed to display silent auction items and make sure they are available and located for installation day of the event. | Décor | Lynn or other volunteers
2 | 2013-09-13 | Identify a photographer |  | need help with this!
2 | 2013-09-13 | Obtain materials and create displays for live auction items. | Live Auction | Mary K., Cita, Mary S., Marilyn K.
2 | 2013-09-13 | Deliver layout and other requirements to venue; include entry tables, auction item tables, raffle table(s), dining room layout and checkout area. Also include number of easels, umbrellas, and café tables and chairs needed and audio visual equipment for both patio and ballroom. Ensure that venue staff knows tables should have table cloths and skirting but should not be skirted together so that they can be moved. | Logistics | Mary S./Lonnie
2 | 2013-09-13 | Make labels for auction tables, bid sheets, tent cards, and programs. | Staff | Cita
2 | 2013-09-13 | Prepare bid sheets-see prior examples for information needed. • Mail merge and print on card stock • Tape metal washers to back to keep them from blowing away. • Make some extra blank ones in case any get lost. • Organize by category and stack with rubber band. | Staff | Cita and Katie
2 | 2013-09-17 | Provide headcount to venue. |  | Mary S., Lonnie
2 | 2013-09-13 | Prepare display cards • Using prior examples as go-by, make a card with the name, brief description, suggested use, item number, name of donor, retail value, and, if appropriate, a photo or graphic. • Add major restrictions, if any. • Small display card for jewelry are tent cards that stand on their own. Some items need larger displays. In the past we have created backing tents out of leftover printed materials and affixed the larger printed displays to the backing tent. • Decide how to secure display cards (washers, two sided tape?) and obtain necessary material. • Organize displays by category. • Put in bins/bags with bid sheets for transport to storage, clearly marked with category. Include stabilization materials. | Staff | Cita and Katie
1 | 2013-09-20 | Work party prepares items for table display (as by preparing wine baskets and baskets for gift certificates and items to be consolidated for sale). Identify all donor-supplied props to ensure return to donor. | Silent Auction | Marilyn, Mary S. and at least two others
1 | 2013-09-25 | Ensure that all materials have been transported to auction storage: • All printed materials (programs, bid sheets, tent cards, auction table labels and dining table numbers) • Display materials such as easels, risers, jewelry props. • Materials to secure displays (double sided tape, sandbags, etc.) • Material needed for décor, such as Kay’s “children” and banners. • Auction supplies, including pencils, cash box, tickets, aprons, table, clipboard (for raffle ticket buyers to note if they want a receipt mailed to them). | Logistics | Susan/Lynn/Cita
0.5 | 2013-09-27 | Deliver wine for serving to venue, attention Shannon. |  | Marilyn
SEE NEXT SHEET FOR DAY-OF LOGISTICS
-1 | 2013-09-30 | Ensure all donors receive handwritten thank you notes. | Live Auction | Mary D
-1 | 2013-09-30 | Ensure all donor-supplie props are returned to the donors | Logistics | Susan
-1 | 2013-09-30 | Handwritten thank you notes to all donors | Silent Auction | Lynn will delegate
-1 | 2013-09-30 | Send tax letter/thank you from CASA | Staff | DD
-1 | 2013-09-30 | Prepare half-page thank-you ad for Sentinel listing all donors and sponsors | Staff | DD

## Day-of Logistics
DAY-OF LOGISTICS
Time | Action | Responsibility | Person(s)
| Deliver wine for serving to bar staff at venue. White wine needs to be delivered in time to get chilled. | Logistics | Marilyn K, will deliver on 9/27 | Décor committee
9:00 | Arrange for all materials to be transported to venue: • All printed materials (programs, bid sheets, tent cards, auction table labels and dining table numbers) (NOTE: You may want to keep the auction table labels and holders separate so that the person directing the truck drivers at the venue can have them with her to set up in advance.) • Display materials such as easels, risers, jewelry props, and lattice supports for artwork if needed. • Materials to secure displays (double sided tape, sandbags, etc.) • Material needed for décor, such as Kay’s “children” and banners. • Auction supplies, including pencils, cash box, tickets, aprons, table, clipboard (for raffle ticket buyers to note if they want a receipt mailed to them). | Logistics | Susan | Logistics
9:00 | Pick up auction items and other materials from storage and deliver to venue. At venue, set up lattice framework to display artwork or posters if needed. | Logistics | Truck/transport volunteers | Logistics
09:30-11:30 | Prepare tables for arrival of auction items; install sign holders and category signs, match bid sheets and tent cards, arrange and secure easels. | Logistics | Set-up volunteers | Logistics
| When materials are delivered, direct items and any props to the table designated for that category. | Logistics |  | Logistics
| Arrange silent auction items on tables; match bid sheets and tent cards with items, add a pencil, discard the pink form; store boxes/bins under the skirted auction tables. Runners will use these to transport items to the check-out area after the auction closes. | Silent Auction |  | Logistics
| Arrange live auction posters and raffle posters on easels or lattice; set up display for dinner auction items if needed. | Logistics |  | Logistics
09:30-11:30 | Transport and install décor | Décor | Jenni/Marilyn M. and 2 décor volunteers | Logistics
12:00-2:00 | Set up wine raffle |  | Friends of CASA
| Set up check-out area | Staff | staff | Logistics/ED
2:30-4:00 | Greet and register guests. | Logistics/Staff | staff/board
| After auction table closes, immediately highlight each final legitimate bid on the bid sheet. (final bid must meet the minimum raise requirement.) | Staff | staff
| After guests leave the patio: • Write up a bid tag for each item (item number, brief description, winning bidder number, final sale price. • Tape yellow copy to the item • White copy and hard copy go to Head Cashier | Staff
| Tabulate bidder totals: • Head cashier distributes white copy of bid tags to front-line cashiers who stable multiple items together and file by bidder number. • Runners bring additional purchases/donations from ballroom and cashiers add these to existing bidder totals, if any. | Staff | Cashiers 1-4
| After auction tables close, direct guests upstairs to ballroom | Logistics | Ushers/spotters
| Greet guests at door of ballroom | Logistics | Board members
| Serve as spotters for live auction and raise the paddle (bids for kids) and for the sale of additional raffle tickets. | Logistics | Ushers/spotters
| After all items are tagged: • Transport items to checkout area and arrange by bidder number. (That way, all items purchased by one bidder will be grouped together.) • Clean everything off tables and move all CASA materials to the green room. • Pack everything in the green room for transport back to CASA. | Staff | Runners
| Record all live auction sales, raise-the-paddle donations, and additional raffle tickets sold in the ballroom. | Staff | Runners
| After close of live auction, guests check out, handing bidder number to the cashier assigned to their number: Cashier 1- checks out bidders 1-54 Cashier 2 – checks out bidders 55-109 Cashier 3 – checks out bidders 110-155 Cashier 4 – checks out bidders 156-220 At checkout: • Retrieve bid tag(s) for guest • Inform bidder of total spent, • Hand tags to runner who retrieves items, • Process payment. (For unresolved issues, give the guest the head cashier’s business card and make a plan to contact the buyer during business hours.) | Staff | Cashiers 1-4
| During checkout: • Take bid tags from cashiers and retrieve item for guest. • After purchase is processed, help guest pack up items for transport. | Staff | Runners